## Lembar1
Penyusunan Test Plan | QA Lead | 24 | 24 | 3
Pembuatan Test Case | Tim QA | 40 | 40 | 5
Unit Testing (Login, Translasi) | Tim QA | 56 | 56 | 7
Integration Testing (Komunitas) | Tim QA, Developer Support | 56 | 56 | 7
System Testing (End-to-End) | QA Lead, Tim QA | 56 | 56 | 7
Bug Fixing & Regression Test | Developer, Tim QA | 32 | 32 | 4
Final Review & Acceptance Test | QA Lead, Product Owner | 24 | 24 | 3
[30 empty] | Task Name | Start Date | End Date | MARET
[5 empty] | Minggu 1 | [6 empty] | Minggu 2 | [6 empty] | Minggu 3 | [6 empty] | Minggu 4 | [6 empty] | Minggu 1 | [6 empty] | Minggu 2 | [6 empty] | Minggu 3 | [6 empty] | Minggu 4
Task Name | Start Date | End Date |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Penyusunan Test Plan |  |  | 3 | -91442 | [25 empty] | Penyusunan Test Plan | 2025-03-01 | 2025-03-03 | 1 | 2 | 3 | bar: Minggu 1 1 to Minggu 1 3
Pembuatan Test Case |  |  | 5 | -91460 | [25 empty] | Pembuatan Test Case | 2025-03-02 | 2025-03-06 |  | 2 | 3 | 4 | 5 | 6 | bar: Minggu 1 2 to Minggu 1 6
Unit Testing (Login, Translasi) |  |  | 7 | -91504 | [25 empty] | Unit Testing | 2025-03-05 | 2025-03-11 |  |  |  |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | bar: Minggu 1 5 to Minggu 2 11
Integration Testing (Komunitas) |  |  | 7 | -91522 | [25 empty] | Integration Testing | 2025-03-07 | 2025-03-13 | [6 empty] | 7 | 8 | 9 | 10 | 11 | 12 | 13 | bar: Minggu 1 7 to Minggu 2 13
System Testing (End-to-End) |  |  | 7 | -91585 | [25 empty] | System Testing (End-to-End) | 2025-03-14 | 2025-03-20 | [13 empty] | 14 | 15 | 16 | 17 | 18 | 19 | 20 | bar: Minggu 2 14 to Minggu 3 20
Bug Fixing & Regression Test |  |  | 4 | -91555 | [25 empty] | Bug Fixing & Regression Test | 2025-03-19 | 2025-03-22 | [18 empty] | 19 | 20 | 21 | 22 | bar: Minggu 3 19 to Minggu 4 22
Final Review & Acceptance Test |  |  | 3 | -91526 | [25 empty] | Final Review & Acceptance Test | 2025-03-23 | 2025-03-24 | [22 empty] | 23 | 24 | bar: Minggu 4 23 to Minggu 4 25
Formulas:
Start Date = DATE(2025,3,LEFT((TEXTJOIN(",",TRUE,[MARET]:BJ12)),FIND(",",(TEXTJOIN(",",TRUE,[MARET]:BJ12)))-1))
End Date = DATE(2025,3,SUBSTITUTE(RIGHT(TEXTJOIN(",",TRUE,[MARET]:BJ12),2),",",""))